## High St. - Mill & Overlay
T/O WESTWOOD - HIGH ST. MILL & OVERLAY PROJECT SCHEDULE
Date | SUNDAY | Date | MONDAY | Date | TUESDAY | Date | WEDNESDAY | Date | THURSDAY | Date | FRIDAY | Date | SATURDAY
2015-04-05 |  | 2015-04-06 | Traffic Control, CF Tube | 2015-04-07 | Traffic Control, CF Tube | 2015-04-08 | Trafic Control, CF Tube | 2015-04-09 | Trafic Control, CF Tube | 2015-04-10 | Trafic Control, CF Tube | 2015-04-11
2015-04-12 | Traffic Control, CF Tube | 2015-04-13 | Traffic Control, CF Tube EB & WB, Strip staging area, stationing | 2015-04-14 | Traffic Control, CF Tube WB, Excavate & Pave Base Rumble Strip STA 256 WB | 2015-04-15 | Traffic Control, CF Tube WB, Pave Binder Rumble St 256 WB | 2015-04-16 | Traffic Control, CF Tube WB, Sawcut Gore Area STA 239 WB | 2015-04-17 | Traffic Control, CF Tube WB, Sawcut Gore area STA 239, 205 WB and Sta 212 EB | 2015-04-18
2015-04-19 |  | 2015-04-20 |  | 2015-04-21 | Traffic Control, Excavate & Pave Gore Area STA 239 WB, Sawcut Gores at Sta 246 & 262 EB | 2015-04-22 | Traffic Control, Excavate & Pave Gore Area STA 205 WB | 2015-04-23 | Traffic Control, CF Tube, Excavate & Pave Gore Area STA 212 EB | 2015-04-24 | Traffic Control, CF Tube, Excavate & Pave Gore Area STA 246 EB | 2015-04-25
2015-04-26 | Traffic Control, CF Tube, Excavate & Pave Gore Area STA 246 EB | 2015-04-27 | Traffic Control, CF Tube, Excavate & Pave Gore Area STA 262 EB | 2015-04-28 | Traffic Control, CF Tube | 2015-04-29 | Traffic Control, CF Tube | 2015-04-30 | Traffic Control, Clearing | 2015-05-01 |  | 2015-05-02
2015-05-03 | Traffic Control, Clearing | 2015-05-04 | Traffic Control, Clearing | 2015-05-05 | Traffic Control, Clearing | 2015-05-06 | Traffic Control, Clearing | 2015-05-07 | Traffic Control Clearing | 2015-05-08 |  | 2015-05-09
2015-05-10 | Traffic Control, Clearing, Milling Sta 112-89+50 WB | 2015-05-11 | Traffic Control, Clearing, Milling Sta 89+50 to 67+00 WB | 2015-05-12 | Traffic Control, Clearing, Milling 2 Crews, Sta 67+00 to 44+50 WB, Sta 205+00 to 185+50 WB | 2015-05-13 | Traffic Control, Clearing, Milling, 2 Crews, Sta 44+50 to 22+00 WB, Sta 185+50 to 160+00 WB | 2015-05-14 | Traffic Control, Clearing & Grubbing, Milling 2 Crews, Sta 22+00 to 262+50 WB , Sta 160+00 to 143+00 WB | 2015-05-15 |  | 2015-05-16
2015-05-17 | Traffic Control, Milling 2 Crews, Sta 262+50 to 240+00 WB , Sta 143+00 to 165+50, AARG Binder Paving Sta 105 to 112 WB Test Strip | 2015-05-18 | Traffic Control, Milling 2 Crews, Sta240+00 to 217+50 WB, Sta 165+50 to 180+00 EB | 2015-05-19 | Traffic Control, Milling 2 crews, Route 30 Ramps, Sta 36+50 to 03+00 WB, Clearing WB | 2015-05-20 | Traffic Control, Milling Sta 03+00 to 248+00 WB, Clearing WB | 2015-05-21 | Traffic Control, Clearing EB, Saw-cutting, Signs, Ramp Paving Rt 30 | 2015-05-22 |  | 2015-05-23
2015-05-24 |  | 2015-05-25 |  | 2015-05-26 | Traffic Control, Shoulder Prep WB | 2015-05-27 | Traffic Control, Shoulder Prep WB, Clearing EB | 2015-05-28 | Traffic Control, Shoulder Prep WB, Saw-cutting | 2015-05-29 | Traffic Control, Shoulder Prep WB, AARG Binder Paving Test Strip Sta 08+00 to 225+00 WB-HS | 2015-05-30
2015-05-31 | Traffic Control, Shoulder Prep, Clearing EB | 2015-06-01 | Traffic Control, Shoulder Prep, Clearing EB | 2015-06-02 | Traffic Control, AARG Binder Paving Test Strip, Milling 2 Crews. Sta 143+00 to 163+00 EB/ Sta 243+0 to 263+00 EB | 2015-06-03 | Traffic Control, Milling 2 Crews. Sta 163+00 to 183+00 EB/ Sta 263+0 to 25+00 EB, Clearing EB | 2015-06-04 | Traffic Control,AARG Binder Pave Sta 113 to 8+00 WB, Milling 2 Crews Sta 183+00 to 203+00 EB / Sta 40+00 to 60+00 EB, Clearing EB | 2015-06-05 |  | 2015-06-06
2015-06-07 | Traffic Control, AARG Binder Pave Sta 88+00 to 63+00 WB, Milllling 2 Crews Sta 203+00 to 223+00 EB / Sta 60+00 to 80+00 EB, Clearing EB | 2015-06-08 | Traffic Control, AARG Binder Paving Sta 63+00 to 38+00 WB, Milllling 2 Crews Sta 223+00 to 243+00 EB / Sta 80+00 to 100+00, Clearing EB | 2015-06-09 | Traffic Control, AARG Binder Paving Sta 38+00 to 13+00 WB, Milllling 2 Crews Sta 243+00 to 263+00 EB / Sta 100+00 to 113+00 EB | 2015-06-10 | Traffic Control, AARG Binder Paving Sta 13+00 to 251+00 WB, Milllling 1 Crew Ramps at Rt 85, Clearing EB | 2015-06-11 | Traffic Control, AARG Binder Paving Sta 251+00 to 226+00 WB, Clearing EB | 2015-06-12 |  | 2015-06-13
2015-06-14 | Traffic Control, AARG Binder Paving Sta 226+00 to 201+00 WB, Clearing EB | 2015-06-15 | Traffic Control, AARG Binder Paving (RAIN OUT)Sta 201+00 to 176+00 WB, Patching EB & WB, Clearing Rt 85 | 2015-06-16 | Traffic Control, AARG Binder Paving Sta 214+00 to 143+00 WB-LS and 143+00 to205+00 EB-HS, Clearing EB Rt 85 | 2015-06-17 | Traffic Control, AARG Binder Paving Sta 205+00 to60+00 EB-HS, Clearing EB, Saw cutting WB | 2015-06-18 | Traffic Control, AARG Binder Paving Sta 60+00 to 113+00 EB-HS and 113+00 to 80+00 EB-BDL, Sawcutting WB | 2015-06-19 | Traffic Control, AARG Binder Paving Sta 80+00 to 05+00 WB-BDL | 2015-06-20
2015-06-21 | Traffic Control, AARG Binder Paving Sta 05+00 to 220+00 WB-BDL, Curb/Berm WB, Sawcutting WB, Hydroseeding WB | 2015-06-22 | Traffic Control, AARG Binder Paving Sta 220+00 to 143+00 WB-BDL, Shoulder Prep EB, Curb/Berm WB, Sawcutting WB | 2015-06-23 | Traffic Control, AARG Binder Paving Sta 143+00 to 245+00 EB-LS, Sawcutting, Curb/Berm WB, Verizon MH WB | 2015-06-24 | Traffic Control, AARG Binder Paving Sta 245+00 to60+00 EB-LS, Sawcutting EB, Curb/Berm WB, Verizon MH WB | 2015-06-25 | Traffic Control, AARG Binder Paving Sta 60+00 to 113+00 EB-LS, Sawcutting EB, Curb/Berm WB, Verizon MH WB | 2015-06-26 | Traffic Control, AARG Binder Paving Sta 143+00 to 185+00 EB-BDL | 2015-06-27
2015-06-28 | Traffic Control, AARG Binder Paving Sta 180+00 to 255+00 EB-BDL, Sawcutting WB, Curb/Berm WB, Verizon MH EB | 2015-06-29 | Traffic Control, AARG Binder Paving Sta 255+00 to 35+00 EB-BDL, Sawcutting EB, Curb/Berm WB, Verizon MH WB | 2015-06-30 | Traffic Control, AARG Binder Paving Sta 35+00 to 113+00 EB-BDL, Sawcutting EB, Curb/Berm WB, Verizon MH EB | 2015-07-01 | Traffic Control, Binder Paving Rt. 85 Ramps EB & WB, Sawcutting WB, Curb/Berm WB, Verizon MH EB | 2015-07-02 | No Work , Day before Holiday | 2015-07-03 | Holiday | 2015-07-04
2015-07-05 | No Work , Day after Holiday | 2015-07-06 | Traffic Control, Binder Paving Rt. 85 Ramps EB & WB, Sawcutting WB, Curb/Berm WB, Verizon MH EB, Structures WB | 2015-07-07 | Traffic Control, Binder Paving Computer Drive Ramps, Sawcutting WB, Curb/Berm WB, Verizon MH EB, Structures WB | 2015-07-08 | Traffic Control, Binder Paving Research Drive Ramps, Sawcutting WB, Curb/Berm WB, Verizon MH EB, Structures WB | 2015-07-09 | Traffic Control, Binder Paving Route 30 Ramps, Sawcutting WB, Curb/Berm WB, Verizon MH EB, Structures WB | 2015-07-10 |  | 2015-07-11
2015-07-12 | Traffic Control, Curb/Berm EB, Verizon MH WB, Structures WB, Guardrail WB | 2015-07-13 | Traffic Control, Curb/Berm EB, Verizon MH WB, Structures WB, Guardrail WB | 2015-07-14 | Traffic Control, Curb/Berm EB, Verizon MH WB, Structures WB, Guardrail WB | 2015-07-15 | Traffic Control, Curb/Berm EB, Verizon MH WB, Structures WB, Guardrail WB | 2015-07-16 | Traffic Control, Curb/Berm EB, Verizon MH WB, Structures WB, Guardrail WB | 2015-07-17 |  | 2015-07-18
2015-07-19 | Traffic Control, Clearing, Berm WB, Verizon MH EB | 2015-07-20 | Traffic Control, Clearing, Berm WB, Verizon MH EB | 2015-07-21 | Traffic Control, Clearing, Berm WB, Verizon MH EB | 2015-07-22 | Traffic Control, Clearing, Berm WB, Verizon MH EB | 2015-07-23 | Traffic Control, Clearing, Berm WB, Verizon MH EB | 2015-07-24 |  | 2015-07-25
2015-07-26 | Traffic Control, Clearing, Edging EB, Verizon MH EB | 2015-07-27 | Traffic Control, Clearing, Edging EB, Verizon MH EB | 2015-07-28 | Traffic Control, Clearing, Edging EB, Verizon MH EB | 2015-07-29 | Traffic Control, Clearing, Edging EB, Verizon MH EB | 2015-07-30 | Traffic Control, Clearing, Edging EB, Patching Edging, Verizon MH EB | 2015-07-31 |  | 2015-08-01
2015-08-02 | Traffic Control, Clearing, Curb Crystal Pond, Berm EB, Verizon MH EB, Traffic Loops, Patch Edging Comp Drive | 2015-08-03 | Traffic Control, Clearing, Edging EB, Berm EB, Verizon MH EB. Traffic Loops, Patch Curb Crystal Pond | 2015-08-04 | Traffic Control, Clearing, Edging EB, Berm WB, Verizon MH EB, Traffic Loops, Patch Edging Research Dr. | 2015-08-05 | Traffic Control, Clearing, Edging Rt 30 ramps, Berm WB, Verizon MH EB, Traffic Loops, Patch Edging EB | 2015-08-06 | Traffic Control, Clearing, Edging Rt 30 ramps, Berm WB, Verizon MH EB, Traffic Loops, Patch Edging EB | 2015-08-07 |  | 2015-08-08
2015-08-09 | Traffic Control, Clearing, Curb Rt 85 Ramps, Berm WB, Verizon MH EB, Guardrail WB, CB Cleaning, Traffic Loops | 2015-08-10 | Traffic Control, Clearing, Curb Patch, Curb Rt 85 Ramps, Verizon MH EB, Grading Shoulders | 2015-08-11 | Traffic Control, Clearing, Curb Patch, Curb Rt 85 Ramps, Verizon MH EB, Grading Shoulders | 2015-08-12 | Traffic Control, Clearing, Curb Patch, Curb Rt 85 Ramps, Verizon MH EB, Grading Shoulders | 2015-08-13 | Traffic Control, Clearing, Curb Rt 85 Ramps, Verizon MH EB, | 2015-08-14 |  | 2015-08-15
2015-08-16 | Traffic Control, Clearing, Curb Patch, Curb Rt 85 Ramps, Guardrail WB, Grading Shoulders | 2015-08-17 | Traffic Control, Clearing, Curb Patch, Curb Rt 85 Ramps, Guardrail WB, Grading Shoulders | 2015-08-18 | Traffic Control, Clearing, Edging EB, Curb Crystal Pond Rd., Guardrail WB, Grading Shoulders | 2015-08-19 | Traffic Control, Grubbing, Curb Patch, Edging Research Ramps, Guardrail WB, Shoulder Grading | 2015-08-20 | Traffic Control, Grubbing, Curb Patch, Guardrail WB , Edging Research Ramps | 2015-08-21 |  | 2015-08-22
2015-08-23 | Traffic Control, Curb Patch, Berm, Guardrail WB | 2015-08-24 | Traffic Control, Curb Patch, Berm | 2015-08-25 | Traffic Control, Curb Patch, Berm, Saw-cutting | 2015-08-26 | Traffic Control, Curb Patch, Shoulder Grading | 2015-08-27 | Traffic Control, Grubbing, Curb Patch | 2015-08-28 |  | 2015-08-29
2015-08-30 | Traffic Control, Curb Patch, Berm, Guardrail Median, Edging Median | 2015-08-31 | Traffic Control, Curb Patch, Berm, Guardrail Median, Curb/Edging Rt 30, Structures WB | 2015-09-01 | Traffic Control, Curb Patch, Guardrail WB, Shoulder Grading, Structures WB | 2015-09-02 | Traffic Control, Grubbing, Curb Patch, Curbing/Edging, Guardrail WB, Shoulder Grading, Structures WB | 2015-09-03 | Traffic Control, Grubbing, Curb Patch, Curbing/Edging, Guardrail WB, Shoulder Grading, Structures WB | 2015-09-04 | No Work , Day before Holiday | 2015-09-05 | No Work , Holiday
2015-09-06 | No Work , Holiday | 2015-09-07 | No Work , Holiday | 2015-09-08 | Traffic Control, Grubbing, Curb Patch, Guardrail WB, Structures EB, Milling WB | 2015-09-09 | Traffic Control, Grubbing, Curb Patch, Guardrail EB, Shoulder Grading, Structures EB, Milling EB | 2015-09-10 | Traffic Control, Grubbing, Curb Patch, Guardrail EB, Shoulder Grading, ARGG Test Strip Paving | 2015-09-11 | Traffic Control, Grubbing, Curb Repairs, Curb Patch, Guardrail EB, Structures EB, Computer Drive Ramp Paving, Temp Tape | 2015-09-12
2015-09-13 | Traffic Control, Grubbing, Curb Repairs, Curb Patch, Guardrail EB, Structures EB, Research Drive Ramp Paving, Temp Tape | 2015-09-14 | Traffic Control, Curb/Edging Repairs, Guardrail EB, Shoulder Grading EB, ARGG WB, Temp Tape | 2015-09-15 | Traffic Control, Curb/Edging Repairs, Guardrail EB, Shoulder Grading EB, ARGG WB, Temp Tape | 2015-09-16 | Traffic Control, Curb/Edging Repairs, Guardrail EB, Shoulder Grading EB, ARGG WB, Temp Tape | 2015-09-17 | Traffic Control, Guardrail EB, Shoulder Grading EB, ARGG WB, Temp Tape | 2015-09-18 | Traffic Control, ARGG WB, Temp Tape | 2015-09-19
2015-09-20 | Traffic Control, Guardrail EB, Shoulder Grading EB, ARGG WB, Temp Tape | 2015-09-21 | Traffic Control, Guardrail EB, Shoulder Grading EB, ARGG WB, Temp Tape | 2015-09-22 | Traffic Control, Guardrail EB, Shoulder Grading EB, ARGG EB | 2015-09-23 | Traffic Control, Guardrail EB, Saw & Seal Layout, Shoulder Grading EB, ARGG EB, Temp Tape, Striping Layout WB | 2015-09-24 | Traffic Control, Guardrail EB, Saw & Seal Layout, Shoulder Grading EB, ARGG EB, Temp Tape, Striping Layout WB | 2015-09-25 | Traffic Control, ARGG EB, Temp Tape | 2015-09-26
2015-09-27 | Traffic Control, Saw & Seal Layout, Shoulder Grading EB, ARGG EB, Temp Tape, Striping Layout WB | 2015-09-28 | Traffic Control, Saw & Seal WB, Shoulder Grading EB, ARGG EB, Temp Tape, Striping Layout WB | 2015-09-29 | Traffic Control, Saw & Seal WB, Shoulder Grading EB, ARGG EB, Temp Tape, Striping Layout WB | 2015-09-30 | Traffic Control, Saw & Seal WB, Shoulder Grading EB, ARGG EB, Temp Tape, Striping Layout WB | 2015-10-01 | Traffic Control, Saw & Seal WB, Shoulder Grading EB, Rt 30 Ramp Paving WB, Temp Tape, Striping Layout WB | 2015-10-02 | Traffic Control, Rt 30 Ramp Paving EB, Temp Tape | 2015-10-03
2015-10-04 | Traffic Control, ARGG EB, Temp Tape | 2015-10-05 | Traffic Control, ARGG EB, Temp Tape | 2015-10-06 | Traffic Control, Guardrail EB, ARGG EB, Temp Tape, Repair pavement EB | 2015-10-07 | Traffic Control, ARGG EB LSL, Temp Tape, Stump removal EB, Berm | 2015-10-08 | Traffic Control, ARGG EB LSL, Temp Tape, Berm | 2015-10-09 | Traffic Control, ARGG EB LSL, Temp Tape | 2015-10-10
2015-10-11 | Holiday | 2015-10-12 | Holiday | 2015-10-13 | Traffic Control, ARGG WB BDL, Temp Tape, Saw and Seal Layout | 2015-10-14 | Traffic Control, ARGG WB BDL, Temp Tape, Concrete nosings, Curb Repair Saw and Seal Layout | 2015-10-15 | Traffic Control, ARGG WB BDL, Temp Tape, Concrete nosings, Curb for Repair and Wheelchair Ramps | 2015-10-16 | Traffic Control, ARGG BDL WB, Saw and Seal Layout WB, Striping Layout WB | 2015-10-17
2015-10-18 | Traffic Control, ARGG BDL WB, Striping Layout WB | 2015-10-19 | Traffic Control, ARGG BDL EB, Saw and Seal Layout WB, Striping Layout WB | 2015-10-20 | Traffic Control, ARGG BDL EB, Saw and Seal Layout WB, Striping Layout WB | 2015-10-21 | Traffic Control, ARGG BDL EB, Saw and Seal Layout WB, Striping Layout WB | 2015-10-22 | Traffic Control, Saw and Seal Layout EB, Striping Layout WB, Prep and Grade for HMA in median | 2015-10-23 | Traffic Control, Saw and Seal Layout EB, Saw and Seal WB, Striping Layout WB, Prep and Grade for HMA in median, W/C Ramps | 2015-10-24 | Traffic Control, Grinding for Striping WB, Striping Layout EB
2015-10-25 | Traffic Control, Grinding for Striping WB, Striping Layout EB, Membrane and Intermediate Course Rt. 30 Bridges, Prep and Grade for HMA, Pave Binder in Median | 2015-10-26 | Traffic Control, Grinding for Striping WB, Striping Layout EB, Top Course Rt. 30 Bridges | 2015-10-27 | Traffic Control, Grinding for Striping WB, Striping Layout EB | 2015-10-28 | Traffic Control, Saw and Seal WB, Grinding for Striping WB, Pave HMA top in median | 2015-10-29 | Traffic Control, Saw and Seal EB, Striping WB, Grinding for Striping EB, Pave HMA top in median | 2015-10-30 | Traffic Control, Saw and Seal EB, Striping WB, Grinding for Striping EB, Prep and Grade for HMA in drives | 2015-10-31 | Traffic Control, Grinding for Striping EB, Striping Layout EB
2015-11-01 | Traffic Control, Saw and Seal EB, Striping WB, Grinding for Striping EB, Prep and Grade for HMA in drives, Milling Mulch/Loam | 2015-11-02 | Traffic Control, Saw and Seal EB, Striping WB, Grinding for Striping EB, Prep and Grade for HMA in drives, Milling Mulch/Loam | 2015-11-03 | Traffic Control, Striping EB, Prep and Grade for HMA in drives, Pave HMA top in drives, milling mulch/loam | 2015-11-04 | Traffic Control, Striping EB, Prep and Grade for HMA in drives, Pave HMA in drives, milling mulch/loam | 2015-11-05 | Traffic Control, Striping EB, Prep and Grade for HMA in drives, Pave HMA in drives, milling mulch/loam | 2015-11-06 | Traffic Control, Striping EB, Prep and Grade for HMA in drives, Pave HMA in drives, milling mulch/loam | 2015-11-07 | Traffic Control, Striping EB
2015-11-08 |  | 2015-11-09 |  | 2015-11-10 |  | 2015-11-11 |  | 2015-11-12 |  | 2015-11-13 |  | 2015-11-14
2015-11-15 |  | 2015-11-16 |  | 2015-11-17 |  | 2015-11-18 |  | 2015-11-19 |  | 2015-11-20 |  | 2015-11-21
2015-11-22 |  | 2015-11-23 |  | 2015-11-24 |  | 2015-11-25 |  | 2015-11-26 |  | 2015-11-27 |  | 2015-11-28
2015-11-29 | Holiday | 2015-11-30 | Pave driveways | 2015-12-01 | Pave driveways, Reflectivity Testing, Loam | 2015-12-02 | Pave driveways, Reflectivity Testing, Loam | 2015-12-03 | Pave driveways, Loam, Striping | 2015-12-04 | Pave driveways, Loam, Striping | 2015-12-05
2015-12-06 | Pave Median, Loam, Guard Rail | 2015-12-07 | Pave Median, Loam, Guard Rail | 2015-12-08 | Pave Median, Loam, Guard Rail | 2015-12-09 | Pave Median, Loam, Guard Rail | 2015-12-10 | Pave Median, Loam, Guard Rail | 2015-12-11 | Pave Median, Loam, Guard Rail | 2015-12-12
2015-12-13 | Loam, Milling Mulch | 2015-12-14 | Loam, Milling Mulch | 2015-12-15 | Loam, Milling Mulch | 2015-12-16 | Loam, Milling Mulch | 2015-12-17 | Loam, Milling Mulch | 2015-12-18 |  | 2015-12-19
2015-12-20 |  | 2015-12-21 |  | 2015-12-22 |  | 2015-12-23 |  | 2015-12-24 |  | 2015-12-25 |  | 2015-12-26
2015-12-27 |  | 2015-12-28 |  | 2015-12-29 |  | 2015-12-30 |  | 2015-12-31 |  | 2016-01-01 |  | 2016-01-02
2016-01-03 |  | 2016-01-04 |  | 2016-01-05 |  | 2016-01-06 |  | 2016-01-07 |  | 2016-01-08 |  | 2016-01-09
2016-01-10 |  | 2016-01-11 |  | 2016-01-12 |  | 2016-01-13 |  | 2016-01-14 |  | 2016-01-15 |  | 2016-01-16
2016-01-17 |  | 2016-01-18 |  | 2016-01-19 |  | 2016-01-20 |  | 2016-01-21 |  | 2016-01-22 |  | 2016-01-23
2016-01-24 |  | 2016-01-25 |  | 2016-01-26 |  | 2016-01-27 |  | 2016-01-28 |  | 2016-01-29 |  | 2016-01-30
2016-01-31 |  | 2016-02-01 |  | 2016-02-02 |  | 2016-02-03 |  | 2016-02-04 |  | 2016-02-05 |  | 2016-02-06
2016-02-07 |  | 2016-02-08 |  | 2016-02-09 |  | 2016-02-10 |  | 2016-02-11 |  | 2016-02-12 |  | 2016-02-13
2016-02-14 |  | 2016-02-15 |  | 2016-02-16 |  | 2016-02-17 |  | 2016-02-18 |  | 2016-02-19 |  | 2016-02-20
2016-02-21 |  | 2016-02-22 |  | 2016-02-23 |  | 2016-02-24 |  | 2016-02-25 |  | 2016-02-26 |  | 2016-02-27
2016-02-28 |  | 2016-02-29 |  | 2016-03-01 |  | 2016-03-02 |  | 2016-03-03 |  | 2016-03-04 |  | 2016-03-05
2016-03-06 |  | 2016-03-07 |  | 2016-03-08 |  | 2016-03-09 |  | 2016-03-10 |  | 2016-03-11 |  | 2016-03-12
2016-03-13 |  | 2016-03-14 |  | 2016-03-15 |  | 2016-03-16 |  | 2016-03-17 |  | 2016-03-18 |  | 2016-03-19
2016-03-20 |  | 2016-03-21 |  | 2016-03-22 |  | 2016-03-23 |  | 2016-03-24 |  | 2016-03-25 |  | 2016-03-26
2016-03-27 |  | 2016-03-28 |  | 2016-03-29 |  | 2016-03-30 |  | 2016-03-31 |  | 2016-04-01 |  | 2016-04-02
2016-04-03 |  | 2016-04-04 |  | 2016-04-05 |  | 2016-04-06 |  | 2016-04-07 |  | 2016-04-08 |  | 2016-04-09
2017-05-21 |  | 2017-05-22 | Digsafe, General Layout | 2017-05-23 |  | 2017-05-24 | Preconstruction Meeting | 2017-05-25 | Erosion Control | 2017-05-26 | Core existing pavement for reclaim, Install barricades | 2017-05-27 | Holiday
2017-05-28 | Holiday | 2017-05-29 | Holiday | 2017-05-30 | Excavate pavement South Apron, Build Staging Area, Mobilize equipment | 2017-05-31 | Excavate pavement South Apron, Survey and Layout | 2017-06-01 | Excavate pavement South Apron, Survey and Layout | 2017-06-02 | Reclaim taxiway and fuel apron pavement | 2017-06-03 | Reclaim taxiway and fuel apron pavement
2017-06-04 |  | 2017-06-05 | Survey and Layout Fuel apron and TaxiwayExcavate excess reclaim, place as subbase in South Apron, Install conduit and junction boxes | 2017-06-06 | Survey and Layout Fuel apron and TaxiwayExcavate excess reclaim, place as subbase in South Apron, Install conduit and junction boxes | 2017-06-07 | Mix reclaim, emulsion, and supplemental aggregate in taxiway and fuel apron, add subbase material in South Apron | 2017-06-08 | Mix reclaim, emulsion, and supplemental aggregate in taxiway and fuel apron, grade subbase material in South Apron | 2017-06-09 | Mix reclaim, emulsion, and supplemental aggregate in taxiway and fuel apron, grade subbase material in South Apron | 2017-06-10 | Pave control strip asphalt in South apron, fine grade reclaim area in taxiway and fuel apron
2017-06-11 |  | 2017-06-12 | Fine grade reclaim area in taxiway and fuel apron | 2017-06-13 | Fine grade reclaim area in taxiway and fuel apron, pave 1st lift asphalt south apron | 2017-06-14 | Pave 1st lift pavement in taxiway and fuel apron | 2017-06-15 | Auger holes and Install tie-downs. Install loops for gates | 2017-06-16 | Auger holes and Install tie-downs. Install loops for gates | 2017-06-17 | Pave top course in south apron
2017-06-18 |  | 2017-06-19 | Pave top course taxiway and fuel apron | 2017-06-20 | Install crushed stone around hangar, Saw and Seal pavement joints, Remove erosion control | 2017-06-21 | Loam and Seed | 2017-06-22 | Loam and Seed | 2017-06-23 | Loam and Seed | 2017-06-24
2017-06-25 |  | 2017-06-26 |  | 2017-06-27 |  | 2017-06-28 |  | 2017-06-29 |  | 2017-06-30 |  | 2017-07-01
2017-07-02 |  | 2017-07-03 | Holiday | 2017-07-04 | Holiday | 2017-07-05 | Excavate sidewalks | 2017-07-06 | Excavate sidewalks | 2017-07-07 | Relocate hydrant Sta | 2017-07-08
2017-07-09 |  | 2017-07-10 | Install new catch basin at Church and Nelson | 2017-07-11 |  | 2017-07-12 | Excavate and install lighting conduit and appurtenances, Survey and layout | 2017-07-13 | Excavate and install lighting conduit and appurtenances, Survey and layout | 2017-07-14 | Excavate and install lighting conduit and appurtenances, Survey and layout | 2017-07-15
2017-07-16 |  | 2017-07-17 | Drop and plate structures to prep for reclaim | 2017-07-18 | Reclaim pavement | 2017-07-19 | Fine grade reclaimed pavement | 2017-07-20 | Fine grade reclaimed pavement | 2017-07-21 | Pave binder course asphalt | 2017-07-22
2017-07-23 |  | 2017-07-24 | Excavate, install new or reset curb | 2017-07-25 | Excavate, install new or reset curb | 2017-07-26 | Fine grade sidewalks | 2017-07-27 | Fine grade sidewalks, pour sidewalks | 2017-07-28 | Pour sidewalks | 2017-07-29
2017-07-30 |  | 2017-07-31 | Milling Melrose St. (Punch List), Structure Adjustments Oread. Adjust structures on Jaques Ave | 2017-08-01 | Mill Indiana, Ida, Greenwood St | 2017-08-02 | Mill Pavement Repairs Greenwood road and sidewalks | 2017-08-03 | Mill Pavement Repairs Greenwood, Control Strip 12.5mm Melrose | 2017-08-04 | Control Strip 9.5 mm Jaques | 2017-08-05
2017-08-06 |  | 2017-08-07 | Punch list Greenwood | 2017-08-08 | Punch list Greenwood | 2017-08-09 | Punch list Greenwood | 2017-08-10 | Mill Salisbury St., Drop and Plate Structures Bjorklund | 2017-08-11 | Mill Salisbury St., Drop and Plate Structures Chester | 2017-08-12
2017-08-13 |  | 2017-08-14 | Bjorklund Full-Depth Mill, Structure adjustments Salisbury | 2017-08-15 | Chester Full-Depth Mill, Grade Bjorklund, Structure adjustments Salisbury | 2017-08-16 | Curb R&R Salisbury, Structure adjustments Salisbury, Pave Binder Bjorklund | 2017-08-17 | Curb R&R Salisbury, Structure adjustments Salisbury, Pave Binder Chester | 2017-08-18 | Curb R&R Salisbury, Structure adjustments Salisbury, Pave Binder Chester | 2017-08-19
2017-08-20 |  | 2017-08-21 | Bituminous Sidewalks Salisbury, Structure adjustments Salisbury | 2017-08-22 | Bituminous Sidewalks Salisbury, Berm Bjorklund | 2017-08-23 | Pave Salisbury, Berm Bjorklund, Chester | 2017-08-24 | Pave Salisbury, Structure Adjustments Bjorklund | 2017-08-25 | Pave Salisbury, Structure Adjustments Chester | 2017-08-26
2017-08-27 |  | 2017-08-28 | Bituminous Sidewalks Bjorklund, Loam and Seed Salisbury | 2017-08-29 | Bituminous Sidewalks Bjorklund, Loam and Seed Salisbury | 2017-08-30 | Bituminous Sidewalks Chester, Loam and Seed Bjorklund, Reg Signs Salisbury | 2017-08-31 | Pave Top Bjorklund, Loam and Seed Chester, Drop and Plate Structures Chiltern Hill North | 2017-09-01 | Pave Top Chester, Drop and Plate Structures Chiltern Hill North | 2017-09-02
2017-09-03 |  | 2017-09-04 | Holiday | 2017-09-05 | Full-Depth Mill Chiltern Hill North, Drop and Plate Structures Grove Heights. | 2017-09-06 | Full Depth Mill Grove-Heights. Grade Chiltern Hill N | 2017-09-07 | Pave Binder Chiltern Hill North, Grade Grove Heights | 2017-09-08 | Drop Structures Hale St., Pave Binder Grove Heights | 2017-09-09
2017-09-10 |  | 2017-09-11 | Full-Depth Mill Hale St., Berm Chiltern Hill North | 2017-09-12 | Bituminous Sidewalks Chiltern Hill N., Berm Chiltern Hill N., Grade Hale St. | 2017-09-13 | Pave Binder Hale St. | 2017-09-14 | Bituminous Sidewalks Chiltern Hill North, Berm Grove Heights | 2017-09-15 | Bituminous Sidewalks Chiltern Hill North, Berm Grove Heights | 2017-09-16
2017-09-17 |  | 2017-09-18 | Adjust Structures Chiltern Hill North, Bituminous Sidewalks Chiltern Hill N | 2017-09-19 | Bituminous Sidewalks Chiltern Hill N., Loam and Seed Chiltern Hill N | 2017-09-20 | Bituminous Sidewalks Hale St., Loam and Seed Chiltern Hill N | 2017-09-21 | Pave Binder Hale St. | 2017-09-22 | Adjust Structures Chiltern Hill North, Bituminous Sidewalks Chiltern Hill North, Berm Hale St. | 2017-09-23
2017-09-24 |  | 2017-09-25 | Adjust Structures Chiltern Hill North, Bituminous Sidewalks Chiltern Hill North, Berm Hale St. | 2017-09-26 | Bituminous Sidewalks Hale St., Loam and Seed Chiltern Hill N | 2017-09-27 | Bituminous Sidewalks Hale St., Loam and Seed Chiltern Hill N | 2017-09-28 | Pave Top Chiltern Hill N, Adjust Structures Hale St. | 2017-09-29 | Berm Grove Heights, Reg Signs Chiltern Hill N | 2017-09-30
2017-10-01 |  | 2017-10-02 | Pave Top Hale St. | 2017-10-03 | Bituminous Sidewalks Grove Heights, Reg Signs Hale | 2017-10-04 | Bituminous Sidewalks Grove Heights | 2017-10-05 | Bituminous Sidewalks Grove Heights | 2017-10-06 | Adjust Structures Grove Heights | 2017-10-07
2017-10-08 |  | 2017-10-09 | Adjust Structures Grove Heights, Full-depth Mill S Lenox | 2017-10-10 | Adjust Structures Grove Heights, Grade S Lenox St. | 2017-10-11 | Loam and Seed Grove Heights, Pave Binder S Lenox St. | 2017-10-12 | Pave Top Grove Heights, Berm S Lenox | 2017-10-13 | Mill Airport Dr., Reg Signs Grove Heights, Concrete Sidewalks S Lenox St. | 2017-10-14
2020-07-12 |  | 2020-07-13 |  | 2020-07-14 |  | 2020-07-15 | PJK-Start excavation of sidewalks/driveways/ wheelchair ramps @ High St & Pond St. | 2020-07-16 | PJK-Excavation of sidewalks/driveways/ wheelchair ramps | 2020-07-17 | PJK-Excavation of sidewalks/driveways/ wheelchair ramps | 2020-07-18
2020-07-19 |  | 2020-07-20 | PJK-Excavation of sidewalks/driveways/ wheelchair ramps | 2020-07-21 | PJK-Excavation of sidewalks/driveways/ wheelchair ramps. MTK- Curb R&R | 2020-07-22 | PJK-Excavation of sidewalks/driveways/ wheelchair ramps. MTK- Curb R&R | 2020-07-23 | PJK-Fine Grade of sidewalks/driveways/ wheelchair ramps. MTK- Curb R&R | 2020-07-24 | PJK-Fine Grade of sidewalks/driveways/ wheelchair ramps. MTK- Pour Concrete WCR/SW/DW | 2020-07-25
2020-07-26 |  | 2020-07-27 | PJK-Fine Grade of sidewalks/driveways/ wheelchair ramps. MTK- Pour Concrete WCR/SW/DW | 2020-07-28 | PJK-Fine Grade of sidewalks/driveways/ wheelchair ramps. MTK- Pour Concrete WCR/SW/DW | 2020-07-29 | PJK-Fine Grade of sidewalks/driveways/ wheelchair ramps. MTK- Pour Concrete WCR/SW/DW | 2020-07-30 | PJK-Start Milling(Walpole Town Line) | 2020-07-31 | PJK-Milling of High St. | 2020-08-01
2020-08-02 |  | 2020-08-03 | PJK-Milling of High St. | 2020-08-04 | PJK-Milling of High St. | 2020-08-05 | PJK-Milling of High St. | 2020-08-06 | PJK-Milling of High St. | 2020-08-07 | PJK-Milling of High St. | 2020-08-08
2020-08-09 |  | 2020-08-10 | PJK-Milling of High St. | 2020-08-11 | PJK-Milling of High St. | 2020-08-12 | PJK-Milling of High St. S.U.R-Adjusting Structures | 2020-08-13 | PJK-Milling of High St. S.U.R-Adjusting Structures | 2020-08-14 | S.U.R-Adjusting Structures Install Traffic loops | 2020-08-15
2020-08-16 |  | 2020-08-17 | S.U.R-Adjusting Structures Install Traffic loops | 2020-08-18 | S.U.R-Adjusting Structures Install Traffic loops | 2020-08-19 | S.U.R-Adjusting Structures Install Traffic loops | 2020-08-20 | PJK-Start Paving High St. | 2020-08-21 | PJK-Paving High St. | 2020-08-22
2020-08-23 |  | 2020-08-24 | PJK-Paving High St. | 2020-08-25 | PJK-Paving High St. | 2020-08-26 | PJK-Paving High St. | 2020-08-27 | PJK-Paving High St. | 2020-08-28 | PJK-Paving High St. | 2020-08-29
2020-08-30 |  | 2020-08-31 | PJK-Paving High St. | 2020-09-01 | PJK-Paving High St. | 2020-09-02 | Line Striping | 2020-09-03 | Line Striping | 2020-09-04 | Line Striping | 2020-09-05
2020-09-06 |  | 2020-09-07 | Line Striping | 2020-09-08 | Asphalt Stamping | 2020-09-09 | Asphalt Stamping | 2020-09-10 | Asphalt Stamping | 2020-09-11 |  | 2020-09-12
2020-09-13 |  | 2020-09-14 |  | 2020-09-15 |  | 2020-09-16 |  | 2020-09-17 |  | 2020-09-18 |  | 2020-09-19
2020-09-20 |  | 2020-09-21 |  | 2020-09-22 |  | 2020-09-23 |  | 2020-09-24 |  | 2020-09-25 |  | 2020-09-26
2020-09-27 |  | 2020-09-28 |  | 2020-09-29 |  | 2020-09-30 |  | 2020-10-01 |  | 2020-10-02 |  | 2020-10-03
2020-10-04 |  | 2020-10-05 |  | 2020-10-06 |  | 2020-10-07 |  | 2020-10-08 |  | 2020-10-09 |  | 2020-10-10
2020-10-11 |  | 2020-10-12 |  | 2020-10-13 |  | 2020-10-14 |  | 2020-10-15 |  | 2020-10-16 |  | 2020-10-17
2020-10-18 |  | 2020-10-19 |  | 2020-10-20 |  | 2020-10-21 |  | 2020-10-22 |  | 2020-10-23 |  | 2020-10-24
2020-10-25 |  | 2020-10-26 |  | 2020-10-27 |  | 2020-10-28 |  | 2020-10-29 |  | 2020-10-30 |  | 2020-10-31
2020-11-01 |  | 2020-11-02 |  | 2020-11-03 |  | 2020-11-04 |  | 2020-11-05 |  | 2020-11-06 |  | 2020-11-07
2020-11-08 |  | 2020-11-09 |  | 2020-11-10 |  | 2020-11-11 |  | 2020-11-12 |  | 2020-11-13 |  | 2020-11-14
2020-11-15 |  | 2020-11-16 |  | 2020-11-17 |  | 2020-11-18 |  | 2020-11-19 |  | 2020-11-20 |  | 2020-11-21
2020-11-22 |  | 2020-11-23 |  | 2020-11-24 |  | 2020-11-25 |  | 2020-11-26 |  | 2020-11-27 |  | 2020-11-28
2020-11-29 |  | 2020-11-30 |  | 2020-12-01 |  | 2020-12-02 |  | 2020-12-03 |  | 2020-12-04 |  | 2020-12-05
2020-12-06 |  | 2020-12-07 |  | 2020-12-08 |  | 2020-12-09 |  | 2020-12-10 |  | 2020-12-11 |  | 2020-12-12
2020-12-13 |  | 2020-12-14 |  | 2020-12-15 |  | 2020-12-16 |  | 2020-12-17 |  | 2020-12-18 |  | 2020-12-19
Formulas:
Date = [Date]+1
Date = [Date, row above]+1